## Instruction
Action plan to continue business in view of COVID-19
This document is a BCP proposal, to be completed by each MFI, to be customized as the actions listed are not exhaustive.
Indeed, each context is different and it is therefore necessary for each MFI to customize this tool.
Please refer also to the document "Attention points business continuity for MFIs in view of the COVID-19 outbreak"
which you can find on the website of ADA
https://www.ada-microfinance.org/en/covid-19-crisis/fiche-covid-19-crisis/2020/03/microfinance-in-front-of-the-covid-19-crisis
Some of the mentioned actions can be performed using the Excel tool "Scenario_maturity_liquidity_gap_BCM".
Further explanation can be found in the memo "Scenario building tools - covid-19".

## Crisis management
Crisis management organisation
Activities / processes | Risks | Attention points / new / adapted activities | Person to act | Current status | Due date
Coordination of the crisis | Lack of coordination, wrong decisions on priorities, indecisiveness, lack of proper communication | Installation of a crisis management team; show strong leadership
| Lack of coordination | Appointment of a crisis coordinator
| Not aware of developments of the outbreak; lack of timely and appropriate actions | Monitor daily the status around the COVID-19 outbreak, logging the results. Take additional measures if necessary (e.g. a highly infected / lock down area)
| Wrong decisions on priorities, indecisiveness | Analysis of critical activities; stopping non urgent activities, e.g. hiring new staff, acquisition of clients, certain projects, certain trainings, ….
| Focusing only on existing way of working | Think out of the box: alternative ways of working, distribution / digital communication channels, new products (emergency lending)
| Focusing only on existing way of working | Establish partnerships with mobile network operators to facilitate mobile. Identify new initiatives or IT solutions that could be used for customers and staff
| Focusing only on existing way of working | Arrange an alternate office to work from in case the Head office is not available anymore.
| Focusing only on existing way of working | Arrange IT facilities to work from home (phone, visioconference, …) - see IT-MIS
Overall HR management | Lack of resources, lack of back up of key staff | Define key staff, especially for senior management / decision makers
Controls | Errors, cutting corners, ignoring controls | Make a business control checklist with daily / weekly actions / controls to be executed: e.g. cleaning branches, communication with stakeholders, liquidity analysis etc.
Insurance | Lack of coordination of insurance policies | Check client’s health/life insurance contracts if any (coverage, claims, processes, etc.) and inform accordingly.
| Lack of coordination of insurance policies | Check insurance for the clients, staff and the institution itself, monitor the insurance claims from clients.
Buildings | Insufficient protection | Close branches or adjust opening hours.
| Insufficient protection | Increase security measures to protect staff and assets. Assign security 24/7.
OTHER ACTIVITIES TO BE COMPLETED BY THE MFI

## Communication
Crisis management communication
Activities / processes | Risks | Attention points / new / adapted activities | Person to act | Current status | Due date
Communication | No clear responsibility for communication | Appointment of a communications manager
Communication | No clear responsibility for communication | Make a communications plan: per stakeholder (see also tab stakeholders) contact details (phone, email, skype, home address, alternative contact details) frequency of the contact (daily, weekly, ad hoc), content, communication channel; use as much as possible non face to face communication via phone / online channels (SMS, USSD, WhatsApp etc.) Keep record of the moments of contact in a logbook
Communication | No complete or up to date contacts | Make a list of contact details of all stakeholders. E.g. make a list of contact details of all staff, funders, authorities; make contact lists per location (HO / Branches / agents)
Communication | Ad hoc communication with Board of Directors | Establish link with the Board of Directors; arrange communication
Communication | No clear responsibility for communication in the branches and areas | Appointment of contact per branch and/or area for the local staff, local authorities, group leaders, social workers, agri workers etc. Update contact details
Communication | Unclarity who to contact at HO | Installing a helpdesk / hotline / central phone number one for staff and one for clients; logging of the calls and put in place the procedure for handling complaints.
Communication | Lack of insight in the situation in the branches and areas | Setting up a daily activity and incident reporting: from HO departments and branches, reporting to the crisis management team
OTHER ACTIVITIES TO BE COMPLETED BY THE MFI

## Stakeholders
Stakeholders
Refer to the memo "Scenario building tools - covid-19", pages 1 to 3 and to the Stakeholder Analysis tab of the Excel "Scenario_maturity_liquidity_gap_BCM".
Activities / processes | Risks | Attention points / new / adapted activities | Person to act | Current status | Due date
Stakeholder management
Dealing with stakeholders | Ignoring stakeholders | Make a stakeholder analysis, identify your stakeholders: e.g. Board of Directors, Staff, Clients, Nat. Microfinance Associations, banks, funders, investors, regulators, tax authorities, outsourcers, third parties, press, ….
Board of Directors | Not adequately involving Board of Directors | Consider to have a member of the Board of Directors part of the crisis team; otherwise frequent communication (see communication tab)
Board of Directors | Not adequately involving Board of Directors | Involve Board of Directors in important decisions
Staff
Communication | Late, incomplete communication | Communicate pro-actively with staff, explain the measures that are taken and actions that are planned. Listen to their worries. See also communication plan separate tab.
Motivation of staff | Demotivated staff, panic | Consider techniques to maintain or improve staff morale (see the WHO note on Coping with stress during the 2019-nCoV outbreak6) and establish an internal communications plan to manage fear and panic. Consider extra payment to staff if that is feasible
Agent banking | Non availability of agent | Identify key locations; arrange for continuity by rotation of agents and/or staff
Training | Infection, illness; lack of resources | Instruct staff to apply the right hygiene measures. Cancel all face to face trainings; postponement if possible; switch to online communication channels; beware of security Continue awareness training, use electronic media as much as possible (SMS, USSD messages / radio / TV). Consult the WHO website for examples: https://www.who.int/emergencies/diseases/novel-coronavirus-2019/advice-for-public)
Warnings | Loss of money for staff | Warn staff against upcoming fraud and scams.
Warnings | Staff taking wrong measures to protect them | Warn staff against rumours / hoax messages
Clients
Communication | Late, incomplete communication | Communicate pro-actively with clients, explain the measures that are taken and actions that are planned. Listen to their worries. See also communication plan separate tab.
Digitalisation | Infection, illness | Promote the use of mobile payments. Consider educating customers to use their e-wallets to avoid touching the cash and to promote social distance.
Awareness | Infection, illness | Continue awareness training, use electronic media as much as possible (SMS, USSD messages / radio / TV). Consult the WHO website for examples. https://www.who.int/emergencies/diseases/novel-coronavirus-2019/advice-for-public)
Awareness | Infection, illness | Make and distribute awareness posters, signs, audio visuals in local languages at the offices.
Services | Infection, illness | Offer other value-added services (safety measures, etc.).
Monitoring clients | Infection, illness | Make an inventory of clients that are ill, monitor the situation.
Warnings | Loss of money for clients | Warn clients against upcoming fraud and scams.
Warnings | Clients taking wrong measures to protect them | Warn clients against rumours / hoax messages
Funders / investors / shareholders
Funders / investor / shareholders management | Breach of covenants | Communication with funders / investors / shareholders to explain the situation; asking for relief. See also communication plan separate tab.
Banks
Communication | Late, incomplete communication | Communication with the banks trying to find out their robustness . See also communication plan and liquidity: separate tabs.
Regulator and local authorities
Compliance with regulatory requirements | Breach of regulatory covenant requirements | Communication with regulators / local authorities to explain the situation; asking for relief. See also communication plan separate tab
Compliance with regulatory requirements | Inadequate monitoring the new COVID-19 measures | Appoint a responsible person; communication according to the communications plan
Compliance with regulatory requirements | Inadequate monitoring the new COVID-19 measures | Execution and monitoring of the implementation
Compliance with regulatory requirements | Inadequate monitoring the new COVID-19 measures | Requesting any necessary waivers
National Microfinance Association (NMA)
Joining forces with MFI's | Not using the leverage of the NMA, being ignored by important stakeholders | Expect the regulatory landscape and national-level measures taken by governments to evolve quickly. Ongoing monitoring is required and should be facilitated by National Microfinance Associations. MFIs should use their associations leverage to: - Proactively discuss and negotiate with regulators coping measures, potential waivers for clients and the MFIs etc. - Find potential credit line facilities, emergency liquidity funds, etc. - Set up collective actions to reduce costs. - Facilitate or assist government or international donors in distributing disaster relief cash to most vulnerable clients. - Start negotiating on potential waivers of covenants and regulatory requirements.
Third parties / outsourcers
Dealing with third parties / outsourcers | Lack of coordination, indecisiveness, lack of proper communication | Appoint a responsible person; communication according to the communications plan
Dealing with third parties / outsourcers | Ignoring third parties / outsourcers | Make an inventory of key suppliers and outsourcers (mobile network operator, internet provider, electricity, MIS/IT etc)
Dealing with third parties / outsourcers | Decline in service levels | Make sure that they adhere to the service levels including BCP measures (preferably laid down in a service level agreement)
Dealing with third parties / outsourcers | Decline in service levels | Look for alternative service providers as back up; see also MIS / IT (tab) and alternative location (tab crisis mgmt.)
Dealing with third parties / outsourcers | Decline in service levels | Monitor the service levels
Dealing with third parties / outsourcers | Breakdown public transport | Arrange timely alternative transport facilities; working from home
OTHER ACTIVITIES TO BE COMPLETED BY THE MFI

## Liquidity
Liquidity management
Activities / processes | Risks | Attention points / new / adapted activities | Person to act | Current status | Due date
Cash flow analysis | Cash shortage short term | Make daily cash flow analysis; analyse which expenses / investments can be put on hold or reduced
Liquidity gap analysis Use the liquidity gap analysis tool in excel "Scenario_maturity_liquidity_gap_BCM". | Liquidity shortage medium term | Make liquidity gap analysis for the next 12 months per month; rest per year ; analyse which expenses / investments can be put on hold or reduced; updating it weekly or bi-weekly
Liquidity monitoring | Being unprepared for new events | Define 3 scenario's including worst case scenario: take actions of stakeholders into account and execute stress testing to assess the absorption capacity Use the excel "Scenario_maturity_liquidity_gap_BCM" and the memo "Scenario building tools - covid-19" to build your scenarios.
Repayments / interest payments by clients | Non repayment by clients | Make an analysis of clients: (not) able/ (not) willing to pay; Able / willing: normal business Able / not willing: zero tolerance, notify the clients Not able to pay / willing to pay: restructuring of loans Not able to pay / not willing to pay: restructuring or write off Even in this crisis, some clients can still earn money or have even increased business and/or continue to have a paid job. So convince these clients to pay their instalments. Use the excel "Assignment -Scenario_maturity_liquidity_gap_BCM_FINAL" and the memo "SCENARIO BUILDING TOOLS - COVID-19" to segment your customer base.
Loan approval / disbursement for clients | Not having enough liquidity | Selection of the clients which loans will not be renewed or to which a smaller loan will be given. Set priorities and exclusion (clients, types of business, regions, branches, etc.) If the MFI has capacity and wishes to continue credit disbursements, specific attention will have to be paid to the financing of the agricultural cycle that starts now in most developing countries.
Client protection | Losing loyalty of clients; mission drift | Ease or suspend repayments / interest payments for clients (if possible).
Client protection | Losing loyalty of clients; mission drift | Consider issuing emergency loans for clients in need (if possible).
Client protection | Losing loyalty of clients; mission drift | Consider free principal / interest payment “holiday” / payment moratoria and late-payment fee waivers.
Client protection | Losing loyalty of clients; mission drift | Consider special rates applied to loans in main affected economic sectors.
Withdrawal of savings / deposits | Mass withdrawal; liquidity problems | Be careful with limiting the withdrawal amount this will affect the trust in the organisation; if no other option limit the maximum amount of the withdrawal
Repayment of loans to funders | Not being able to repay | Ask for restructuring of the loan, repayment holiday and, emergency facilities
Funding | Withdrawal or non renewal of funding; lack of liquidity | Look for support from funders, investors and NGO's
Investors | Lack of liquidity | Ask for extra capital injection
Liquid assets with the bank | Bank puts a cap on withdrawals or a stop on withdrawals | Spread your liquid assets over more banks
OTHER ACTIVITIES TO BE COMPLETED BY THE MFI

## HR management
HR management
Activities / processes | Risks | Attention points / new / adapted activities | Person to act | Current status | Due date
Key staff | Failing to continue in case of non-availability of staff | Arrange back up staff for key staff and arrange necessary sharing of knowledge; non sharing of the same office space between these two
Key staff | Failing to continue in case of non-availability of staff | Arrange signature authorisations for the back up staff; inform IT to update system authorisations
Key staff | Failing to continue in case of non-availability of staff | Consider staff rotation where possible / cross training
Staff activites | Infection, illness; lack of resources | Identification of vulnerable staff (age 60+, diabetes, obese, asthma, cardio vascular disease, HIV, pregnant women); be prepared to shift work if possible / necessary
Staff activites | Infection, illness; lack of resources | Consider working in shifts (team A, team B crew) for those that need to be present in the office building; who can be deployed at different work schedules.
Staff activites | Infection, illness; lack of resources | Encourage staff to avoid big groups, social gatherings, mass gatherings/crowded places (markets, cinema, religious places, stations, bus-stands, public places) and public transport.
Working from home | Infection, illness; lack of resources | Working from home as much as possible; online meetings; no or limited travel
Working from home | Infection, illness; lack of resources | Employees that have fever and/or other Covid-19 related symptoms must stay at home, reporting to HR.
Working from home | Unclear guidance | Establish or revise a “working from home” policy. To be decided by management. Be prepared to apply to all employees in case of partial or full lockdown.
Staff activites | Unclear guidance | Check the HR policies and make adjustments where necessary (working from home, sick leave, holiday, extra compensation, travel, hygiene measures etc.)
Staff activites | Unclear guidance | Monitor illness of staff
Staff activites | Demotivation of staff | Consider extra payment for staff to keep them motivated
Staff activites | Idle staff / work load not balanced | Reconsider the HR capacity, adjust where necessary. For staff who have leave to take and whose absence will not impact on business continuity, place them on administrative leave as soon as possible. Monitor closely the number of staff working from home and staff that is reported to be ill.
OTHER ACTIVITIES TO BE COMPLETED BY THE MFI

## Health
Health management
Activities / processes | Risks | Attention points / new / adapted activities | Person to act | Current status | Due date
Protection gear | Infections of staff | Buy enough stock health and safety facilities like hand sanitizers, medical gloves, soap and/or alcohol-based rub. Disposable tissues for cleaning purposes.
Protection gear | Infections of staff | Arrange protection for teller staff like plastic foil or Perspex screen to separate the teller from the clients.
Protection gear | Infections of staff | For tellers, security guards and loan officers: wear medical gloves; make sure that there is enough stock. Tellers: because physical cash (notes and coins) can be contaminated with the virus
Protection gear | Infections of staff | Use masks when deemed necessary
Social distancing | Infections of staff | Cancel all face to face meetings; switch to online communication channels; beware of security
Social distancing | Infections of staff | Maintain at least 1.5 meter (“two arm’s length”) between people (social distancing) inside and outside the office
Social distancing | Infections of staff | Social distancing; mark distance of the floor / use tape to make separation; limit the number of staff / visitors in a small room.
Hygiene | Insufficient cleaning of the building | Increase hygiene measures. Cleaning / disinfecting the offices and frequently touched surfaces on a regular base; more frequent regular cleaning and ventilate the buildings
Hygiene | Insufficient personal hygiene | Provide a system for washing hands with soap and water or with alcohol-based rub at the entrance to the agencies, instruct to wash the hands thoroughly (washing your hands properly takes about as long as singing "Happy Birthday" twice, health posters how to wash hands
Hygiene | Insufficient personal hygiene | Avoid any biometric devise usage for the time being
Hygiene | Insufficient personal hygiene | Follow the health instructions
Illness | Unable to detect / prevent illness | Temperature measurement of staff / visitors before entering the office building. Entry to building to be refused in case of fever.
Illness | Unable to detect / prevent illness | Staff that feel ill and have the symptoms and/or are tested positive must remain at home for at least 14 days.
Illness | Unable to detect / prevent illness | Staff members that feel well but have a sick family member at home with COVID-19 should stay at home as well for at least 14 days.
Illness | Unable to detect / prevent illness | Inform direct colleagues if they have been in contact with the infected staff member
Illness | Unable to detect / prevent illness | If the staff member has been at the office: intensified cleaning of the office
Buildings | Unable to detect / prevent illness | Close branches in an affected area – staff is prohibited to go to the affected area.
Buildings | Unable to detect / prevent illness | Entry of visitors restricted to HO office unless absolutely necessary.
Buildings | Unable to detect / prevent illness | Prepare for closing access to clients to the branches if required.
OTHER ACTIVITIES TO BE COMPLETED BY THE MFI

## IT-MIS
IT - MIS - technical communication
Activities / processes | Risks | Attention points / new / adapted activities | Person to act | Current status | Due date
Working from home | Not being able to work from home | Implement facilities to work from home (company laptops, VPN connections, mobile phones) and test (!) with the respective staff.
Working from home | Not being able to work from home | Arrange and test (!) ICT / MIS continuity measures (backups, UPS, generators with enough fuel).
Working from home | Not being able to work from home | Test video conferencing facilities.
Key staff back up | Lack of key staff availability | Arrange for system authorisation for the back up staff
Digitalisation clients | Not being able to communicate with clients | Identify digital means / IT solutions that could be used to communicate with clients (SMS, internet site, …)
Digitalisation clients | Use of cash | Identify digital means / IT solutions that could be used for clients (wallet, ..)
OTHER ACTIVITIES TO BE COMPLETED BY THE MFI

## Public & policy actions
Actions of public, press, social media, government
Activities / processes | Risks | Attention points / new / adapted activities | Person to act | Current status | Due date
Actions of the public | Political unrest / protests / rioting / blockades / robbery / plundering | Increase security measures; follow the news and take precautionary measures to protect the buildings against rioting. Inform the staff about these developments.
Famine | Political unrest / protests / rioting / blockades / robbery / plundering | Coordinate actions with the NMA's; ask support from international support organisations
Social media / press | Spreading rumours | Monitor the news; be prepared, actions in communication plan
Politicians promote a “non-payment” movement. | Non payment by clients | Coordinate actions with the NMA's; daily monitoring of new measures / regulations of the government;
OTHER ACTIVITIES TO BE COMPLETED BY THE MFI

## Macro economy
Macro economy
Activities / processes | Risks | Attention points / new / adapted activities | Person to act | Current status | Due date
Monitoring macro economy | Interest goes up / down | Execute liquidity analysis and stress testing
Monitoring macro economy | FX risk: depreciation of the local currency | Execute liquidity analysis and stress testing
Monitoring macro economy | Value chain stagnation commodities / raw material affecting the institutions / affecting the business of the clients | Execute liquidity analysis and stress testing
Monitoring macro economy | Price increase of basic needs | Execute liquidity analysis and stress testing
Monitoring macro economy | Slowdown of remittances | Execute liquidity analysis and stress testing
OTHER ACTIVITIES TO BE COMPLETED BY THE MFI

## Status (hidden)
Ready
Ongoing on schedule
Ongoing , delay
Not started
Non applicable